## 2009 09
Department |  | Trained | Templates Completed | EMR Utilization | Overall Deployment | Est.Completion Date
Family Medicine |  | 98%-(53/54) | 100%-(13/13) | 98%-(52/53) | 99.07%
OBGYN |  | 84%-(86/102) | 95%-(52/55) | 99%-(85/86) | 93.06%
Internal Medicine |  | 70%-(92/132) | 61%-(11/18) | 24%-(22/92) | 53.96%
Medical Records |  | 33%-(6/18) | 0%-(0/0) | 0%-(0/0) | 8.25%
Ophthalmology |  | 0%-(0/0) | 100%-(3/3) | 0%-(0/0) | 50%
UBCC |  | 0%-(0/0) | 0%-(0/21) | 0%-(0/0) | 0%
Pediatrics |  | 0%-(0/0) | 100%-(20/20) | 0%-(0/0) | 50%
Surgery |  | 0%-(0/0) | 0%-(0/18) | 0%-(0/0) | 0%
Neuropsychiatry |  | 0%-(0/0) | 0%-(0/15) | 0%-(0/0) | 0%
Orthopedics |  | 0%-(0/0) | 0%-(0/0) | 0%-(0/0) | 0%
Radiology |  | 0%-(0/0) | 0%-(0/0) | 0%-(0/0) | 0%
Emergency Medicine |  | 0%-(0/0) | 0%-(0/0) | 0%-(0/0) | 0%
Interface Timelines |  | Completed | Projected Due Date | Comments
UMC(Thomason)
| Results Only | 100% | 2008-12-01
| Bi-Directional | 0% | TBD
Quest
| Results Only | 0% | 2010-01-01
| Bi-Directional | 0% | 2010-05-01
| E-pharmacy | 0% | 2010-05-01
Labcorp
| Results Only | 0% | TBD
| Bi-Directional | 0% | 2010-12-30
Radiology/PACS Interface |  | Milestones | Action Items | Projectued Due Date | Comments
| UMC |  | Set up conference call with DSS/UMC for initial discussion |  | DSS will make all necessary resources available